# Standard Operating Procedure: Ground Truth (GT) Task Handling

## Purpose

This SOP establishes the standard process for handling new Ground Truth tasks to ensure consistent communication, quality control, and protocol adherence across all team members.

## Background

GT task requirements vary from project to project and dataset to dataset. Rules, border handling methods, and specific protocols change based on what is being tested. This variability requires a structured onboarding process for each new task.

## Roles

### Task Owner

The individual (typically the project lead) who defines task requirements and provides feedback.

### Tester(s)

1-2 designated team members who:

- Are the first to work on a new GT task

- Test initial protocols

- Submit early work for feedback

- Serve as the primary contact with the Task Owner

### Team Members

All tracers who will work on the task, including those who may not work on it directly but should be aware of protocol changes.

## Standard Process

### 1. Initial Task Introduction

Historical Method (In-Person):

- Task Owner presents the task directly to the team

- Team asks clarifying questions on the spot

Current Method (Remote):

- Communication via Slack or Zoom

- Questions documented and addressed asynchronously

### 2. Tester Assignment

- Designate 1-2 team members as testers for the new task

- Testers serve as front person(s) for initial protocol development

- Selection should consider experience and availability

### 3. Initial Testing Phase

- Tester(s) complete a portion of the task before others begin

- Work is done following initial instructions and best judgment

- Document any unclear areas or questions that arise

### 4. Early Submission & Feedback

- Tester(s) submit their initial work to the Task Owner early

- Purpose: Identify areas needing more attention and validate approach

- Task Owner reviews and provides feedback on initial interpretation

### 5. Full Team Task Delivery Meeting

Format: Zoom meeting with entire team

Attendees:

- All team members who will work on the task

- Team members who won't work directly on it but need awareness of protocol changes

- Task Owner

- Tester(s)

Agenda:

- Review feedback from early submission

- Clarify protocols and requirements

- Address questions from all team members

- Demonstrate specific techniques if needed (borders, tracing methods, etc.)

- Document final protocols

### 6. Task Execution

- All team members follow protocols established in the delivery meeting

- Tester(s) serve as first point of contact for questions

- Escalate unclear issues to Task Owner via Slack/Zoom

## Communication Channels

### Primary: Slack

- Quick questions

- Clarifications

- Status updates

### Secondary: Zoom

- Complex explanations

- Visual demonstrations

- Full team meetings

## Key Principles

- Variability is Expected: Each task may have different requirements

- Test Before Scale: Always use tester(s) to validate approach before full team engagement

- Document Changes: Keep team informed of protocol updates

- Inclusive Communication: Include all team members in delivery meetings, even if not directly working on the task

## Complaint Prevention

To avoid misunderstandings:

- Always use the testing phase before full team deployment

- Ensure all team members attend delivery meetings

- Document task-specific requirements clearly

- Maintain open communication channels

- Don't assume protocols from previous tasks apply to new ones

## Document Control

Created: [Nov 5, 2025]
Last Updated: [Nov 5, 2025]
Owner: [Benjamin Silverman]
Review Frequency: As needed when processes change

This SOP should be referenced whenever a new GT task is introduced to ensure consistent onboarding and quality standards.